## Sheet1
| Dept | Account | Estimating | Premedia | Creative Services |  |  | Production |  |  | DMG |  |  | Strategy |  | Ops
| Division |  |  |  | Project Management | Creative | Copy | DTP | Proof | Image | Project Management | Development | Production | Planning | Analytics | Acct/Finance | HR | IT
Milestones | Task
Job Initiation | Estimate Request
Project Description
Specs/Requirements Doc
Schedules
Campaign Strategy: Historical Data/Pre-Planning
Estimates
Job Code(s)
Assign Resources
Set up Sources, Repositories, Tracking
Fulfillment Plan (Print) /Deployment & Launch Plan (DMG)
Creative Rounds | Creative Brief/SOW
This is an iterative process | Internal Kick Off
that repeats based on | Design Concepts
project requirements. | Copy Concepts
Campaign Strategy: Segmentation Plan
Production Design
Image Planning/Asset Gathering
CR Release
Internal Creative Review (WTW)
Campaign Strategy: Prelim Matrix
Client Review
Revisions
Creative Approval
First Round Variants
Design Concepts: Sitemap (DMG)
Second Round Variants
Design Concepts: Wireframes (DMG)
Photo Shoot | Photo shoot
Image Selects
Production Rounds | Internal Production Review (WTW)
This is an iterative process | Deliverables List
that repeats based on | CR-Final/RD[X-1] Revisions
project requirements. | Creative Execution across project
Image Acquisition & Composition
Production Design (Architecture & Dev)
Proof Reading (Content Management)
Production Edits & Revisions
ROUND[X] Release
Release for Color
First Round Variants
Order Clipping Paths
Cold Read, Mockups
Test Site (DMG)
Final/Release Round Variants
Campaign Strategy: Final Matrix
Client Approval
Production Checklist
File Release to Premedia/QA
Premedia=>InHome | Release for Confirmer Color
PRINT | Campaign Segmentation Review
Confirmer Approval
DBL Review
Print & Mail Matrix
Final Specs & Paper
DBL Approval
Postage
On Press
Mail Drops
InHome
QA=>Launch | Move from Dev to QA environment
DMG | UAT/Standards internal review
Production Revisions
QA Approval
Analytics In Place
Email/Banner Variants
Release To Blast House/Banner Host
MicroSite/Static Site Variants
Release To host/ops for launch
App/Dynamic Site Variants
Move QA to Production environment
Project Close | Archiving
Post Mortem
Analytics